## Sheet1
Week | Starting Data | End Date | Functions of Web | Done | Functions of Mobile | Done
W1 | 2019-07-04 | 2019-07-11 | Welcome Page |  | Home Page
|  |  | Employee Registration |  | Login Page(front end)
Asset Registration
View Assets(Asset pool)
W2 | 2019-07-11 | 2019-07-18 | Booking Assets |  | Dashboard
|  |  | View Employees- update(+Demote,promote,delete) |  | View Assets(Asset pool)
|  |  | View owned Assets |  | View owned Assets
|  |  | Home Page |  | View employees
W3 | 2019-07-18 | 2019-07-25 | Employee's Dashboard |  | Report damages(+QR scanning)
View Assets(Asset pool)
View owned Assets
|  |  | Asset Manager (Delete assets,update assets) |  | Welcome page
W4 | 2019-07-25 | 2019-08-01 | Empl' Request assets |  | Request assets
|  |  | Empl'Booking Assets |  | Notifications
Final Report preparing
W5 | 2019-08-01 | 2019-08-08 | Report Damages |  | booking assets
|  |  | View Damages |  | sign in process
Notifications -1
Final Report preparing
W6 | 2019-08-08 | 2019-08-15 | Sign in
Generating Reports
Notifications -2
Final Report preparing